## Cover Page
Version of STP
Date of Approval
MIS Code
Start-up Time Plan and Procurement Plan
2nd Call for Proposals
|  | Project title: | Policies for Enhancing Access to Health Services in Deprived Areas
|  | Project acronym: | The Healthy Municipality | [5 empty] | Pr.Axis4
|  | Priority Axis: | 4. A Socially Inclusive Cross-Border Area
|  | Investment Priority: | (9a) | Investing in health and social infrastructure which contribute to national, regional and local development, reducing inequalities in terms of health status, promoting social inclusion through improved access to social, cultural and recreational services and the transition from institutional to community-based services.
|  | Project duration: | Project Start date: | 2017-11-01 | Project End date: | 2019-10-31 | Total Months | 23.9507
|  | WP Title |  |  |  | Start date: | End date: | Total months
| WP1 | Project Management and Coordination |  |  |  | 2017-11-01 | 2019-10-31 | 23.9507
| WP2 | Communication and Publicity activities |  |  |  | 2017-11-01 | 2019-10-31 | 23.9507
| WP3 | Stocktaking |  |  |  | 2018-01-01 | 2018-11-30 | 10.9405
| WP4 | Developing Tools - Early Warning System |  |  |  | 2018-04-01 | 2019-01-31 | 10.0205
| WP5 | Designing Local Prevention Policy and Pilot Testing |  |  |  | 2018-10-01 | 2019-07-31 | 9.9548
| WP6 | Evaluation and Mainstreaming |  |  |  | 2019-06-01 | 2019-10-31 | 4.9938
[5 empty] | Start-up period end : | 2018-04-30 | Start-up period duration(6-9 months) | 6
| B. Nr. | Beneficiary title |  |  |  |  | Country | Budget
| LB (PB1) | Regional Development Agency of Rodopi S.A. |  |  |  |  | Greece | 107318.4
| PB2 | Aristotle University of Thessaloniki-Special Account for Research Funds - Department of Economics |  |  |  |  | Greece | 68975
| PB3 | Municipality of Arriana |  |  |  |  | Greece | 168759
| PB4 | Municipality of Iasmos |  |  |  |  | Greece | 162453
| PB5 | Agency for Transnational Training and Development |  |  |  |  | Greece | 72864
| PB6 | Regional Health Inspectorate |  |  |  |  | Bulgaria | 53378
| PB7 | Association of Rhodope Municipalities |  |  |  |  | Bulgaria | 51282
| PB8 | Municipality of Krumovgrad |  |  |  |  | Bulgaria | 226623
| PB9 | Municipality of Momchilgrad |  |  |  |  | Bulgaria | 223495
PB10
[7 empty] | Total Project budget | 1135147.4
Lead Beneficiary Stamp and Signature

## START-UP-PLAN
START-UP PLAN PROJECT THE HEALTHY MUNICIPALITY
LB (PB1) |  | Regional Development Agency of Rodopi S.A. |  |  |  | 2017 |  | 2018
WP | Deliv. | Name Deliverable/actions | start date | end date | duration | November | December | January | February | March | April | May | June | July | August | September | October | November | December
WP1 | 1.1.3 | Establishing and Operating Project Management Structures for each Partner | 2017-11-01 | 2019-10-31 | 24 | Setting up Project Team | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions
WP1 | 1.1.5 | External evaluation | 2018-04-01 | 2019-10-31 | 19 | [9 empty] | Signing Contract | Assigning work | Evaluating project | Evaluating project | Evaluating project
WP2 | 2.1.2 | Project web site | 2017-11-01 | 2018-12-31 | 14 | [7 empty] | Preparing and Running Tender 1 | Preparing and Running Tender 1 | Signing Contract | Developing portal | Maintaing website | Maintaing website | Maintaing website
WP2 | 2.1.5 | Local information seminars in partner areas | 2017-11-01 | 2018-12-31 | 15 | [7 empty] | Preparing and Running Tender 1 | Preparing and Running Tender 1 | Signing Contract - Preparing seminar | Holding seminar
WP3 | 3.1.5 | Designing digital maps on morbidity and health infra structure | 2018-06-01 | 2019-03-31 | 9 | [7 empty] | Preparing and Running Tender 1 | Preparing and Running Tender 1 | Signing Contract
WP4 | 4.1.3 | Digital municipal health platform in each area | 2018-06-01 | 2018-12-31 | 7 | [7 empty] | Preparing and Running Tender 1 | Preparing and Running Tender 1 | Signing Contract
WP5 | 5.1.2 | Setting up common cross border prevention plan for pilot testing | 2018-11-01 | 2019-01-31 | 3 | [7 empty] | Preparing and Running Tender 1 | Preparing and Running Tender 1 | Signing Contract
WP5 | 5.1.3 | Designing and applying communication actions for applying commn plan in project areas | 2019-02-01 | 2019-07-30 | 6 | [7 empty] | Preparing and Running Tender 1 | Preparing and Running Tender 1 | Signing Contract
WP6 | 6.1.2 | Synthesis report and results on application of pilot application in entire cross border area (problems and good practices) | 2019-08-01 | 2019-09-30 | 2 | [7 empty] | Preparing and Running Tender 1 | Preparing and Running Tender 1 | Signing Contract
WP6 | 6.1.4 | Setting up cross border lab on prevention and primary health policies | 2019-07-01 | 2019-10-31 | 4 | [7 empty] | Preparing and Running Tender 1 | Preparing and Running Tender 1 | Signing Contract
PB2 |  | Aristotle University of Thessaloniki-Special Account for Research Funds - Department of Economics |  |  |  | 2017 |  | 2018
WP | Deliv. | Name Deliverable/actions | start date | end date | duration | November | December | January | February | March | April | May | June | July | August | September | October | November | December
WP1 | 1,2,2 | Establishing and Operating Project Management Structures for each Partner | 2017-11-01 | 2019-10-31 | 24 |  | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions
WP1 | 1,2,4 | 6 transnational meetings | 2018-01-01 | 2019-08-31 | 20 |  |  | Participating at Meeting |  |  |  |  | Participating at Meeting |  |  | Participating at Meeting
WP1 | 1,2,5 | External evaluation | 2018-04-01 | 2019-10-31 | 19 | [10 empty] | Assigning work | Evaluating project | Evaluating project | Evaluating project
WP2 | 2,2,4 | Kick off and closing conferences | 2018-06-01 | 2019-09-30 | 16 | [7 empty] | Participating at conference
WP2 | 3,2,1 | Population socioeconomic characteristics and operating health infra structure (desk analysis in each area) | 2018-03-01 | 2018-11-30 | 9 |  |  |  |  | Μethodology of study | Collecting material | Collecting material | Collecting material | Processing material | Processing material | Conducting deliverable | Conducting deliverable | Conducting deliverable | Conducting deliverable
WP2 | 3,2,2 | Research (questionnaire): Access to and degree of needs’ coverage of health services in partners' areas | 2018-01-01 | 2018-11-30 | 11 |  |  |  | Designing methodology | Selecting sample | Selecting sample | Selecting sample | Processing material | Processing material | Processing material | Conducting deliverable | Conducting deliverable | Conducting deliverable | Conducting deliverable
WP3 | 3,2,4 | Synthesis Reports for each partner area and for the entire cross border area | 2018-11-01 | 2019-02-28 | 4 | [12 empty] | Conducting report | Conducting report
WP4 | 4,2,2 | Digital data base in each area with patient cards and digital alert system | 2018-11-01 | 2019-03-31 | 5 | [10 empty] | Preparing and Running Tender 1 | Running Tender 1 - Assigning contract | Implementing deliverable | Implementing deliverable
PB3 |  | Municipality of Arriana |  |  |  | 2017 |  | 2018
WP | Deliv. | Name Deliverable/actions | start date | end date | duration | November | December | January | February | March | April | May | June | July | August | September | October | November | December
WP1 | 1,3,2 | Establishing and Operating Project Management Structures for each Partner | 2017-11-01 | 2019-10-31 | 24 | Setting up Project Team | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions
WP3 | 3,3,3 | Sampling on identifying local morbidity in project areas | 2018-03-01 | 2018-09-30 | 7 | [9 empty] | Preparing tender 1 | Running tender 1 | Running tender 1 | Assigning contract | Conducting examinations
WP4 | 4,3,3 | Digital municipal health platform in each area | 2018-06-01 | 2018-12-31 | 7 | [8 empty] | Preparing and Running tender 3 | Assigning contract | Purchasing equipment
WP4 | 4,3,4 | Supply of additional equipment for health centers | 2018-04-01 | 2018-08-31 | 5 | [8 empty] | Preparing and Running tender 3 | Assigning contract | Purchasing equipment
WP5 | 5,3,4 | Pilot application in each area | 2019-02-01 | 2019-07-30 | 6 | [9 empty] | Preparing tender 1 | Running tender 1 | Running tender 1 | Assigning contract
|  | Deliverables 2.3.5, 4.3.5, 5.3.3, 6.3.3, 6.3.4 | 2018-09-01 | 2019-10-31 | 14 | [8 empty] | Preparing Tender 2 | Preparing Tender 2 | Running Tender 2 | Running Tender 2 | Assigning contract
PB4 |  | Municipality of Iasmos |  |  |  | 2017 |  | 2018
WP | Deliv. | Name Deliverable/actions | start date | end date | duration | November | December | January | February | March | April | May | June | July | August | September | October | November | December
WP1 | 1,4,2 | Establishing and Operating Project Management Structures for each Partner | 2017-11-01 | 2019-10-31 | 24 | Setting up Project Team | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions
WP3 | 3,4,3 | Sampling on identifying local morbidity in project areas | 2018-03-01 | 2018-09-30 | 7 | [9 empty] | Preparing tender 1 | Running tender 1 | Running tender 1 | Assigning contract | Conducting examinations
WP4 | 4,4,3 | Digital municipal health platform in each area | 2018-06-01 | 2018-12-31 | 7 | [8 empty] | Preparing and Running tender 3 | Assigning contract | Purchasing equipment
WP4 | 4,4,4 | Supply of additional equipment for health centers | 2018-04-01 | 2018-08-31 | 5 | [8 empty] | Preparing and Running tender 3 | Assigning contract | Purchasing equipment
WP5 | 5,4,4 | Pilot application in each area | 2018-02-01 | 2018-10-31 | 9 | [9 empty] | Preparing tender 1 | Running tender 1 | Running tender 1 | Assigning contract
|  | Deliverables 2.4.5, 4.4.5, 5.4.3, 6.4.3, 6.4.4 | 2018-09-01 | 2019-10-31 | 14 | [8 empty] | Preparing Tender 2 | Preparing Tender 2 | Running Tender 2 | Running Tender 2 | Assigning contract
PB5 |  | Agency for Transnational Training and Development |  |  |  | 2017 |  | 2018
WP | Deliv. | Name Deliverable/actions | start date | end date | duration | November | December | January | February | March | April | May | June | July | August | September | October | November | December
WP1 | 1,5,2 | Establishing and Operating Project Management Structures for each Partner | 2017-11-01 | 2019-10-31 | 24 | Setting up Project Team | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions
WP1 | 1,5,4 | 6 transnational meetings | 2017-11-01 | 2019-08-31 | 22 |  |  | Participating at Meeting |  |  |  |  | Participating at Meeting |  |  | Participating at Meeting
WP1 | 1,5,5 | External evaluation | 2018-07-01 | 2019-10-31 | 16 | [10 empty] | Assigning work | Evaluating project | Evaluating project | Evaluating project
WP2 | 2,5,3 | Publicity material | 2018-05-01 | 2019-10-31 | 19 | [6 empty] | Designing Material | Designing Material | Designing Material | Designing Material | Designing Material | Designing Material | Designing Material | Designing Material
WP2 | 2,5,4 | Kick off and closing conferences | 2018-06-01 | 2019-09-30 | 16 | [7 empty] | Participating at conference
WP3 | 3,5,1 | Population socioeconomic characteristics and operating health infra structure (desk analysis in each area) | 2018-03-01 | 2018-11-30 | 9 |  |  |  |  | Designing methodology | Collecting material | Collecting material | Call for recruiting staff | Running call - Staff recruitment | Processing material | Writing deliverable | Writing deliverable | Writing deliverable
WP3 | 3,5,2 | Research (questionnaire): Access to and degree of needs’ coverage of health services in partners' areas | 2018-01-01 | 2018-11-30 | 11 | [7 empty] | Call for recruiting staff | Running call - Staff recruitment | Preparing questionnaires | Collecting material | Processing material | Writing deliverable
WP3 | 3,5,4 | Synthesis Reports for each partner area and for the entire cross border area | 2018-11-01 | 2019-02-28 | 4 | [7 empty] | Call for recruiting staff | Running call - Staff recruitment |  |  |  | Conducting report
PB6 |  | Regional Health Inspectorate |  |  |  | 2017 |  | 2018
WP | Deliv. | Name Deliverable/actions | start date | end date | duration | November | December | January | February | March | April | May | June | July | August | September | October | November | December
WP1 | 1,6,2 | Establishing and Operating Project Management Structures for each Partner | 2017-11-01 | 2019-10-31 | 24 | [6 empty] | Setting up Project Team | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions
WP1 | 1,6,4 | 6 transnational meetings | 2017-11-01 | 2019-08-31 | 22 | [6 empty] | Organizing Meeting | Holding meeting
WP2 | 2,6,4 | Kick off and closing conferences | 2018-06-01 | 2019-09-30 | 16 | [6 empty] | Preparing conference | Holding conference
WP3 | 3,6,1 | Population socioeconomic characteristics and operating health infra structure (desk analysis in each area) | 2018-03-01 | 2018-11-30 | 9 | [8 empty] | Running tender 3 | Conducting survey | Conducting survey | Conducting survey
WP3 | 3,6,2 | Research (questionnaire): Access to and degree of needs’ coverage of health services in partners' areas | 2018-01-01 | 2018-11-30 | 11 | [8 empty] | Setting up team | Designing methodology | Developing tools | Selecting sample | Selecting sample
|  | Deliverables 3.6.4, 4.6.1, 5.6.2, 6.6.3, 6.6.4 | 2018-01-01 | 2018-11-30 | 11 | [8 empty] | Running tender 3 | Assigning contract
|  | Deliverables 4.6.2, 4.6.3 | 2018-06-01 | 2018-12-31 | 7 | [10 empty] | Running tender 4
PB7 |  | Association of Rhodope Municipalities |  |  |  | 2017 |  | 2018
PB7 |  | #REF! |  |  |  | November | December | January | February | March | April
WP | Deliv. | Name Deliverable/actions | start date | end date | duration | November | December | January | February | March | April | May | June | July | August | September | October | November | December
WP1 | 1,7,2 | Establishing and Operating Project Management Structures for each Partner | 2017-11-01 | 2019-10-31 | 24 | Setting up Project Team | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Setting up Project Team after the approved modifications | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions
WP1 | 1,7,4 | 6 transnational meetings | 2017-11-01 | 2019-08-31 | 22 | Participating at Meeting |  | Participating at Meeting
WP2 | 2,7,3 | Publicity material | 2018-01-01 | 2019-10-31 | 22 |  |  | Designing Material - Preparing tender 1 - Running tender 1 | Designing Material - Running tender 1 - Signing Contract | Designing Material | Designing Material |  |  | Designing Material - Preparing tender 1 - Running tender 1 | Designing Material - Running tender 1 - | Designing Material -Running tender 1 - Signing Contract | Designing Material | Designing Material | Designing Material
WP5 | 5,7,1 | Designing local health policy plans | 2018-10-01 | 2019-03-31 | 6 | [10 empty] | Designing local health policy plan -Preparing tender 2 - Running tender 2 | Designing local health policy plan - Running tender 2 - Signing contract | Designing local health policy plan | Designing local health policy plan
WP5 | 5,7,3 | Designing and applying communication actions for applying common plan in project areas | 2019-02-01 | 2019-07-31 | 6 | [10 empty] | Designing and applying communication actions for applying common plan in project areas -Preparing tender 2 - Running tender 2 | Designing and applying communication actions for applying common plan in project areas - Running tender 2 - Signing contract
WP6 | 6,7,1 | Evaluating results of pilot application at local level | 2019-06-01 | 2019-08-31 | 3 | [10 empty] | Evaluating results of pilot application at local level -Preparing tender 2 - Running tender 2 | Evaluating results of pilot application at local level -Running tender 2 - Signing contract
PB8 |  | Municipality of Krumovgrad |  |  |  | 2017 |  | 2018
PB7 |  | #REF! |  |  |  | November | December | January | February | March | April
WP | Deliv. | Name Deliverable/actions | start date | end date | duration | November | December | January | February | March | April | May | June | July | August | September | October | November | December
WP1 | 1,8,2 | Establishing and Operating Project Management Structures for each Partner | 2017-11-01 | 2019-10-31 | 24 | Setting up Project Team | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions
WP1 | 1,8,4 | 6 transnational meetings | 2017-11-01 | 2019-08-31 | 22 | [6 empty] | Preparing tender 2 | Running tender 2 - Participating at Meeting | Assigning contract
WP1 | 1,8,5 | External evaluation | 2018-04-01 | 2019-10-31 | 19 |  |  |  |  | Preparing tender 2 | Running tender 2 | Assigning work | Evaluating project | Evaluating project | Evaluating project | Evaluating project | Evaluating project | Evaluating project | Evaluating project
WP3 | 3,8,3 | Sampling on identifying local morbidity in project areas | 2018-03-01 | 2018-09-30 | 7 | [6 empty] | Preparing tender 4 | Running tender 4 | Running tender 4 | Running tender 4 | Running tender 4 | Assigning contract - Conducting examinations
WP4 | 4,8,2 | Digital data base in each area with patient cards and digital alert system | 2018-06-01 | 2018-12-31 | 7 | [5 empty] | Preparing Tender 8 | Running Tender 8 | Running Tender 8 -Assigning contract
WP4 | 4,8,3 | Digital municipal health platform in each area | 2018-06-01 | 2018-12-31 | 7 |  |  |  | Preparing tender 6 | Running tender 6 | Running tender 6 | Assigning contract
WP4 | 4,8,4 | Supply of additional equipment for health centers (IT hardware and software) | 2018-04-01 | 2018-12-31 | 9 |  |  |  | Preparing tender 6 | Running tender 6 | Assigning contract
WP4 | 4,8,4 | Supply of additional equipment for health centers (furnitures) | 2018-04-01 | 2018-12-31 | 9 |  |  | Preparing tender 9 | Running tender 9 | Running tender 9 | Assigning contract
WP4 | 4,8,4 | Supply of additional equipment for health centers (medical equipment) | 2018-04-01 | 2018-12-31 | 9 |  |  | Preparing tender 9 | Running tender 9 | Running tender 9 | Assigning contract
WP4 | 4,8,4 | Supply of additional equipment for health centers (ambulance) | 2018-04-01 | 2018-12-31 | 9 | [5 empty] | Preparing tender 7 | Running tender 7 | Running tender 7 | Running tender 8 | Running tender 9 | Assigning contract
WP4 | 4,8,4 | Supply of additional equipment for health centers (infrastructure works) | 2018-04-01 | 2018-12-31 | 9 |  | Preparing and Running tender 5 | Running tender 5 | Running tender 5 | Running tender 5 | Running tender 5 | Assigning contract
WP5 | 5,8,4 | Pilot application in project areas | 2019-02-01 | 2019-07-31 | 6 | [6 empty] | Preparing tender 4 | Running tender 4 | Running tender 4 | Running tender 4 | Running tender 4 | Assigning contract
|  | Deliverables 2.8.5, 4.8.5, 5.8.3, 1.8.4 | 2018-06-01 | 2019-10-31 | 17 | [5 empty] | Preparing tender 3 | Running tender 3 | Assigning contract
PB9 |  | Municipality of Momchilgrad |  |  |  | 2017 |  | 2018
PB7 |  | #REF! |  |  |  | November | December | January | February | March | April
WP | Deliv. | Name Deliverable/actions | start date | end date | duration | November | December | January | February | March | April | May | June | July | August | September | October | November | December
WP1 | 1,9,2 | Establishing and Operating Project Management Structures for each Partner | 2017-11-01 | 2019-10-31 | 24 | Setting up Project Team | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions | Monitoring Actions
WP1 | 1,9,4 | 6 transnational meetings | 2017-11-01 | 2019-08-31 | 22 | Participating at Meeting | [9 empty] | Preparing tender 2 | Running tender 2 - Assigning contract - Participating at Meeting
WP3 | 3,9,3 | Sampling on identifying local morbidity in project areas | 2018-03-01 | 2018-09-30 | 7 | [9 empty] | Preparing tender 3 | Running tender 3 | Running tender 3 | Running tender 3 | Assigning contract - Conducting examinations
WP4 | 4,9,2 | Digital data base in each area with patient cards and digital alert system | 2018-06-01 | 2018-12-31 | 7 | [13 empty] | Preparing Tender 8
WP4 | 4,9,3 | Digital municipal health platform in each area | 2018-06-01 | 2018-12-31 | 7 | [10 empty] | Preparing and Running tender 6 | Running tender 6 | Assigning contract
WP4 | 4,9,4 | Supply of additional equipment for health centers (Medical equipment) | 2018-04-01 | 2018-12-31 | 9 | [7 empty] | Preparing tender 4 | Running tender 4 | Running tender 4 | Running tender 4 | Assigning contract - starting works
WP4 | 4,9,4 | Supply of additional equipment for health centers (repair works and elevator delivery) | 2018-04-01 | 2018-12-31 | 9 |  |  |  | Preparing tender 5 | Running tender 5 | Running tender 5 | Assigning contract | Purchasing equipment
WP5 | 5,9,4 | Pilot application in project areas | 2019-02-01 | 2019-07-31 | 6 | [13 empty] | Preparing tender 2
WP6 | 6,9,3 | Adapting local plans to results of pilot application | 2019-08-01 | 2019-10-31 | 3 | [13 empty] | Preparing tender 7
|  | Deliverables 2.9.5, 4.9.5, 5.9.3, | 2018-01-01 | 2019-08-31 | 20 | [9 empty] | Preparing tender 2 | Running tender 2 | Running tender 2 | Assigning contract

## LB (PB1)
|  | Project Lead Beneficiary (PB1) | Regional Development Agency of Rodopi S.A. |  | Project Start date: | 2017-11-01
|  | Beneficiary Country | Greece |  | Project End date: | 2019-10-31 |  |  |  | ,
|  | Total Beneficiary budget in AF | 107318.4 |  | Project duration (months): | 23.9507
|  | Total Amount to be procured | 107318.4 |  | Start-up period end: | 2018-04-30
WP | Del. | Budget line | Brief description of the tender- Steps to be followed, etc | Tender Nr. | Type of tender | Amount of tender (€) | Estimated Date of launching (MM/YYYY) | Estimated Date of tender closure (MM/YYYY) | Estimated Date of Contract granting (MM/YYYY) | Estimated tender Procedure duration (months) | Milestone to be achieved within start-up period
WP1 | D1.1.3 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 25 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 1 | Open | 1000 | 2018-06-15 | 2018-07-16 | 2018-07-31 | 1.5 | Completion of tender and begin of works
WP1 | D1.1.4 | External Expertise and Services |  | Not required | Own means | 100 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.1.2 | External Expertise and Services |  | Tender 1 | Open | 8500 | 2018-06-15 | 2018-07-16 | 2018-07-31 | 1.5 | Completion of tender and begin of works
WP3 | D3.1.5 | External Expertise and Services |  | Tender 1 | Open | 12000 | 2018-06-15 | 2018-07-16 | 2018-07-31 | 1.5 | Completion of tender and begin of works
WP4 | D4.1.3 | External Expertise and Services |  | Tender 1 | Open | 18000 | 2018-06-15 | 2018-07-16 | 2018-07-31 | 1.5 | Completion of tender and begin of works
WP2 | D2.1.5 | External Expertise and Services |  | Tender 1 | Open | 1390 | 2018-06-15 | 2018-07-16 | 2018-07-31 | 1.5 | Completion of tender and begin of works
WP5 | D5.1.2 | External Expertise and Services |  | Tender 1 | Open | 6000 | 2018-06-15 | 2018-07-16 | 2018-07-31 | 1.5 | Completion of tender and begin of works
WP5 | D5.1.3 | External Expertise and Services |  | Tender 1 | Open | 1300 | 2018-06-15 | 2018-07-16 | 2018-07-31 | 1.5 | Completion of tender and begin of works
WP6 | D6.1.2 | External Expertise and Services |  | Tender 1 | Open | 7000 | 2018-06-15 | 2018-07-16 | 2018-07-31 | 1.5 | Completion of tender and begin of works
WP6 | D6.1.4 | External Expertise and Services |  | Tender 1 | Open | 5350 | 2018-06-15 | 2018-07-16 | 2018-07-31 | 1.5 | Completion of tender and begin of works
WP1 | D1.1.5 | External Expertise and Services | 1. Signing Contract | Not required |  | 2000 |  |  | 2018-08-01 |  | Signing contract Starting works
WP1 | D1.1.1 | Staff Costs | No tender procedure is required. | Not required | Own means | 6555 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.1.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 3268 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.1.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 2408 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.1.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 1200 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.1.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 730.8 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.1.1 | Staff Costs | No tender procedure is required. | Not required | Own means | 2800 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.1.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 1400 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.1.5 | Staff Costs | No tender procedure is required. | Not required | Own means | 2070.6 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.1.5 | Staff Costs | No tender procedure is required. | Not required | Own means | 2400 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.1.5 | Staff Costs | No tender procedure is required. | Not required | Own means | 2100 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.1.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 1400 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.1.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 2113.5 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.1.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 2113.5 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.1.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 3800 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.1.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 1900 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.1.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 2800 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.1.2 | Office and Administration | No tender procedure is required. | Not required | Own means | 851 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.1.1 | Office and Administration | No tender procedure is required. | Not required | Own means | 781 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.1.2 | Office and Administration | No tender procedure is required. | Not required | Own means | 268 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.1.5 | Office and Administration | No tender procedure is required. | Not required | Own means | 261 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.1.5 | Office and Administration | No tender procedure is required. | Not required | Own means | 1246 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.1.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 315 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.1.4 | Office and Administration | No tender procedure is required. | Not required | Own means | 307 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.1.1 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 100 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.1.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 380 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.1.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 260 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.1.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 500 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.1.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 70 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.1.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 80 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.1.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 200 |  |  |  |  | No milestones are to be achieved in the start-up period.
Note on E7: Georgios Charalampous: You will have to unite tenders of similar services/equipmnet to the minimum necessary regardless of the WPs or Actions that these may belong. Use the same nr (1,2,3) for the tenders you include in each line of the excel file if you plan to have them released under one procedure. The final number should be the number of the tenders you plan release in total.
Note on F7: Georgios Charalampous: Specify the type of the tender (open, restricted, direct, etc). The programme strongly advises the beneficiaries to use the maximum level of publicity. It is recommneded that for all the tenders of one budget line the type of the tender that coresponds to the total amount allocated to the budget line is followed.
Note on G7: Georgios Charalampous: The amount corresponding to the specific tender
Note on H7: Georgios Charalampous: The expected date of the tender release.
Note on I7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date tender closure
Note on J7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date of contract signature
Note on K7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): From the date of the tender launching until the contract signature
Note on L7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Explain the milestone to be achieved for this tender within the start-up period

## PB2
|  | Project Beneficiary 2 (PB2) | Aristotle University of Thessaloniki-Special Account for Research Funds - Department of Economics |  | Project Start date: | 2017-11-01
|  | Beneficiary Country | Greece |  | Project End date: | 2019-10-31
|  | Total Beneficiary budget in AF | 68975 |  | Project duration (months): | 23.9507
|  | Total Amount to be procured | 68975 |  | Start-up period end: | 2018-04-30
WP | Del. | Budget line | Brief description of the tender- Steps to be followed, etc | Tender Nr. | Type of tender | Amount of tender (€) | Estimated Date of launching (MM/YYYY) | Estimated Date of tender closure (MM/YYYY) | Estimated Date of Contract granting (MM/YYYY) | Estimated tender Procedure duration (months) | Milestone to be achieved within start-up period
WP4 | D4.2.2 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 1 | Direct | 5000 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | No milestones are to be achieved in the start-up period
WP2 | D2.2.4 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 2 | Direct | 3000 | 2019-06-01 | 2019-06-30 | 2019-07-31 | 2 | No milestones are to be achieved in the start-up period
WP1 | D1.2.5 | External Expertise and Services | 1. Signing Contract | Not required |  | 2000 |  |  | 2018-09-01 |  | Signing contract Starting works
WP6 | D6.2.4 | External Expertise and Services | No tender procedure is required. | Not required | Own means | 350 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.2.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 2752 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.2.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 2236 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.2.1 | Staff Costs | No tender procedure is required. | Not required | Own means | 7200 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.2.1 | Staff Costs | No tender procedure is required. | Not required | Own means | 1500 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.2.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 3600 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.2.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 5400 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.2.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 3000 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.2.1 | Staff Costs | No tender procedure is required. | Not required | Own means | 3960 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.2.1 | Staff Costs | No tender procedure is required. | Not required | Own means | 1500 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.2.1 | Staff Costs | No tender procedure is required. | Not required | Own means | 11979 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.2.1 | Staff Costs | No tender procedure is required. | Not required | Own means | 5994 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.2.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 3600 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.2.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 1800 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.2.1 | Office and Administration | No tender procedure is required. | Not required | Own means | 577 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.2.1 | Office and Administration | No tender procedure is required. | Not required | Own means | 1161 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.2.2 | Office and Administration | No tender procedure is required. | Not required | Own means | 596 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.2.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 430 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.2.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 330 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.2.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 600 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.2.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 100 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.2.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 110 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.2.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 200 |  |  |  |  | No milestones are to be achieved in the start-up period.
Note on E7: Georgios Charalampous: You will have to unite tenders of similar services/equipmnet to the minimum necessary regardless of the WPs or Actions that these may belong. Use the same nr (1,2,3) for the tenders you include in each line of the excel file if you plan to have them released under one procedure. The final number should be the number of the tenders you plan release in total.
Note on F7: Georgios Charalampous: Specify the type of the tender (open, restricted, direct, etc). The programme strongly advises the beneficiaries to use the maximum level of publicity. It is recommneded that for all the tenders of one budget line the type of the tender that coresponds to the total amount allocated to the budget line is followed.
Note on G7: Georgios Charalampous: The amount corresponding to the specific tender
Note on H7: Georgios Charalampous: The expected date of the tender release.
Note on I7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date tender closure
Note on J7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date of contract signature
Note on K7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): From the date of the tender launching until the contract signature
Note on L7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Explain the milestone to be achieved for this tender within the start-up period

## PB3
|  | Project Beneficiary 3 (PB3) | Municipality of Arriana |  | Project Start date: | 2017-11-01
|  | Beneficiary Country | Greece |  | Project End date: | 2019-10-31
|  | Total Beneficiary budget in AF | 168759 |  | Project duration (months): | 23.9507
|  | Total Amount to be procured | 168759 |  | Start-up period end: | 2018-04-30
WP | Del. | Budget line | Brief description of the tender- Steps to be followed, etc | Tender Nr. | Type of tender | Amount of tender (€) | Estimated Date of launching (MM/YYYY) | Estimated Date of tender closure (MM/YYYY) | Estimated Date of Contract granting (MM/YYYY) | Estimated tender Procedure duration (months) | Milestone to be achieved within start-up period
WP1 | D1.3.4 | External Expertise and Services | No tender procedure is required. | Not required | Own means | 100 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.3.3 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 35 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 1 | Open | 34500 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | Completion of tender start of works
WP5 | D5.3.4 | External Expertise and Services |  | Tender 1 | Open | 45000 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | Completion of tender
WP2 | D2.3.5 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 2 | Direct | 1300 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | Launch of Tender
WP4 | D4.3.5 | External Expertise and Services |  | Tender 2 | Direct | 1200 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | Launch of Tender
WP5 | D5.3.3 | External Expertise and Services |  | Tender 2 | Direct | 3050 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | Launch of Tender
WP6 | D6.3.3 | External Expertise and Services |  | Tender 2 | Direct | 4500 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | Launch of Tender
WP6 | D6.3.4 | External Expertise and Services |  | Tender 2 | Direct | 350 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | Launch of Tender
WP4 | D4.3.3 | Equipment | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 25 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 3 | Restricted | 2800 | 2018-07-01 | 2019-07-31 | 2019-08-31 | 2 | Completion of tender
WP4 | D4.3.4 | Equipment |  | Tender 3 | Restricted | 50000 | 2018-07-01 | 2019-07-31 | 2019-08-31 | 2 | Completion of tender start of works
WP1 | D1.3.5 | External Expertise and Services | 1. Signing Contract | Not required |  | 3000 |  |  | 2018-10-31 |  | Signing contract Starting works
WP1 | D1.3.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 4816 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.3.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 5160 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.3.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 900 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.3.5 | Staff Costs | No tender procedure is required. | Not required | Own means | 1001 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.3.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 600 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.3.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 1680 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.3.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 600 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.3.5 | Staff Costs | No tender procedure is required. | Not required | Own means | 1050 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.3.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 700 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.3.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 700 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.3.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 540 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.3.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 600 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.3.2 | Office and Administration | No tender procedure is required. | Not required | Own means | 1296 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.3.5 | Office and Administration | No tender procedure is required. | Not required | Own means | 150 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.3.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 128 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.3.2 | Office and Administration | No tender procedure is required. | Not required | Own means | 468 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.3.5 | Office and Administration | No tender procedure is required. | Not required | Own means | 150 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.3.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 210 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.3.4 | Office and Administration | No tender procedure is required. | Not required | Own means | 179 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.3.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 81 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.3.4 | Office and Administration | No tender procedure is required. | Not required | Own means | 90 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.3.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 380 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.3.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 260 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.3.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 500 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.3.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 100 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.3.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 220 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.3.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 400 |  |  |  |  | No milestones are to be achieved in the start-up period.
Note on E7: Georgios Charalampous: You will have to unite tenders of similar services/equipmnet to the minimum necessary regardless of the WPs or Actions that these may belong. Use the same nr (1,2,3) for the tenders you include in each line of the excel file if you plan to have them released under one procedure. The final number should be the number of the tenders you plan release in total.
Note on F7: Georgios Charalampous: Specify the type of the tender (open, restricted, direct, etc). The programme strongly advises the beneficiaries to use the maximum level of publicity. It is recommneded that for all the tenders of one budget line the type of the tender that coresponds to the total amount allocated to the budget line is followed.
Note on G7: Georgios Charalampous: The amount corresponding to the specific tender
Note on H7: Georgios Charalampous: The expected date of the tender release.
Note on I7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date tender closure
Note on J7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date of contract signature
Note on K7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): From the date of the tender launching until the contract signature
Note on L7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Explain the milestone to be achieved for this tender within the start-up period

## PB4
|  | Project Beneficiary 4 (PB4) | Municipality of Iasmos |  | Project Start date: | 2017-11-01
|  | Beneficiary Country | Greece |  | Project End date: | 2019-10-31
|  | Total Beneficiary budget in AF | 162453 |  | Project duration (months): | 23.9507
|  | Total Amount to be procured | 162453 |  | Start-up period end: | 2018-04-30
WP | Del. | Budget line | Brief description of the tender- Steps to be followed, etc | Tender Nr. | Type of tender | Amount of tender (€) | Estimated Date of launching (MM/YYYY) | Estimated Date of tender closure (MM/YYYY) | Estimated Date of Contract granting (MM/YYYY) | Estimated tender Procedure duration (months) | Milestone to be achieved within start-up period
WP3 | D3.4.3 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 35 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 1 | Open | 34500 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | Completion of tender start of works
WP5 | D5.4.4 | External Expertise and Services |  | Tender 1 | Open | 45000 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | Completion of tender
WP2 | D2.4.5 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 2 | Direct | 1300 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | Launch of Tender
WP4 | D4.4.5 | External Expertise and Services |  | Tender 2 | Direct | 1200 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | Launch of Tender
WP5 | D5.4.3 | External Expertise and Services |  | Tender 2 | Direct | 3050 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | Launch of Tender
WP6 | D6.4.3 | External Expertise and Services |  | Tender 2 | Direct | 4500 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | Launch of Tender
WP6 | D6.4.4 | External Expertise and Services |  | Tender 2 | Direct | 350 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | Launch of Tender
WP4 | D4.4.3 | Equipment | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 25 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 3 | Restricted | 2800 | 2018-07-01 | 2019-07-31 | 2019-08-31 | 2 | Completion of tender
WP4 | D4.4.4 | Equipment |  | Tender 3 | Restricted | 50000 | 2018-07-01 | 2019-07-31 | 2019-08-31 | 2 | Completion of tender start of works
WP1 | D1.4.5 | External Expertise and Services | 1. Signing Contract | Not required |  | 2000 |  |  | 2018-10-31 |  | Signing contract Starting works
WP1 | D1.4.4 | External Expertise and Services | No tender procedure is required. | Not required | Own means | 100 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.4.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 4816 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.4.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 1800 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.4.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 900 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.4.5 | Staff Costs | No tender procedure is required. | Not required | Own means | 1001 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.4.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 600 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.4.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 1680 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.4.5 | Staff Costs | No tender procedure is required. | Not required | Own means | 1050 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.4.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 700 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.4.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 540 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.4.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 600 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.4.2 | Office and Administration | No tender procedure is required. | Not required | Own means | 596 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.4.5 | Office and Administration | No tender procedure is required. | Not required | Own means | 144 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.4.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 128 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.4.2 | Office and Administration | No tender procedure is required. | Not required | Own means | 468 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.4.5 | Office and Administration | No tender procedure is required. | Not required | Own means | 150 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.4.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 210 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.4.4 | Office and Administration | No tender procedure is required. | Not required | Own means | 179 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.4.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 81 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.4.4 | Office and Administration | No tender procedure is required. | Not required | Own means | 90 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.4.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 380 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.4.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 260 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.4.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 500 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.4.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 160 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.4.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 220 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.4.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 400 |  |  |  |  | No milestones are to be achieved in the start-up period.
Note on E7: Georgios Charalampous: You will have to unite tenders of similar services/equipmnet to the minimum necessary regardless of the WPs or Actions that these may belong. Use the same nr (1,2,3) for the tenders you include in each line of the excel file if you plan to have them released under one procedure. The final number should be the number of the tenders you plan release in total.
Note on F7: Georgios Charalampous: Specify the type of the tender (open, restricted, direct, etc). The programme strongly advises the beneficiaries to use the maximum level of publicity. It is recommneded that for all the tenders of one budget line the type of the tender that coresponds to the total amount allocated to the budget line is followed.
Note on G7: Georgios Charalampous: The amount corresponding to the specific tender
Note on H7: Georgios Charalampous: The expected date of the tender release.
Note on I7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date tender closure
Note on J7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date of contract signature
Note on K7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): From the date of the tender launching until the contract signature
Note on L7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Explain the milestone to be achieved for this tender within the start-up period

## PB5
|  | Project Beneficiary 5 (PB5) | Agency for Transnational Training and Development |  | Project Start date: | 2017-11-01
|  | Beneficiary Country | Greece |  | Project End date: | 2019-10-31
|  | Total Beneficiary budget in AF | 72864 |  | Project duration (months): | 23.9507
|  | Total Amount to be procured | 68624 |  | Start-up period end: | 2018-04-30
WP | Del. | Budget line | Brief description of the tender- Steps to be followed, etc | Tender Nr. | Type of tender | Amount of tender (€) | Estimated Date of launching (MM/YYYY) | Estimated Date of tender closure (MM/YYYY) | Estimated Date of Contract granting (MM/YYYY) | Estimated tender Procedure duration (months) | Milestone to be achieved within start-up period
WP2 | D2.5.3 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 1 | Direct | 11700 | 2019-02-01 | 2019-02-28 | 2019-03-15 | 1.5 | No milestones are to be achieved in the start-up period.
WP6 | D6.5.4 | External Expertise and Services | No tender procedure is required. | Not required | Direct | 350 |  |  | 2019-09-01 |  | No milestones are to be achieved in the start-up period.
WP1 | D1.5.5 | External Expertise and Services | 1. Signing Contract | Not required |  | 2000 |  |  | 2018-09-01 |  | No milestones are to be achieved in the start-up period.
WP1 | D1.5.2 | Staff Costs | Current Staff - Jr. Consultant - No tender procedure is required. | Not required | Own means | 2835.68 |  |  |  |  | Starting works
WP2 | D2.5.3 |  |  |  |  | 1724.4 |  |  |  |  | Starting works
WP2 | D2.5.3 |  |  |  |  | 2845.26 |  |  |  |  | Starting works
WP3 | D3.5.1 |  |  |  |  | 1724.4 |  |  |  |  | Starting works
WP1 | D1.5.2 | Staff Costs | Current Staff - Sr. Consultant - No tender procedure is required. | Not required | Own means | 1700 |  |  |  |  | Starting works
WP3 | D3.5.1 |  |  |  |  | 3100 |  |  |  |  | Starting works
WP3 | D3.5.4 |  |  |  |  | 2000 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.5.1 |  |  |  |  | 2400 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.5.2 |  |  |  |  | 1900 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.5.3 |  |  |  |  | 1020 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.5.4 |  |  |  |  | 740 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.5.1 | Staff Costs | Staff recruitment - Economist | Tender 2 | Call for recruiting staff | 4165 | 2018-06-15 | 2018-07-07 | 2018-07-15 | 1 | No milestones are to be achieved in the start-up period.
WP3 | D3.5.2 | Staff Costs |  |  |  | 2805 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.5.4 | Staff Costs |  |  |  | 3400 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.5.1 | Staff Costs |  |  |  | 1020 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.5.2 | Staff Costs |  |  |  | 1020 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.5.3 | Staff Costs |  |  |  | 2040 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.5.4 | Staff Costs |  |  |  | 1190 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.5.2 | Staff Costs | Staff recruitment - Statistical Analyst |  |  | 948 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.5.2 | Staff Costs | Staff recruitment - Recearchers |  |  | 6480 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.5.2 | Staff Costs | Staff recruitment - Local research coordinator |  |  | 960 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.5.2 | Staff Costs | Staff recruitment - Data entry |  |  | 1920 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.5.2 | Staff Costs | Staff recruitment - Informatics expert |  |  | 276 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.5.2 | Office and Administration | No tender procedure is required. | Not required | Own means | 676.26 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.5.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 478 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.5.1 | Office and Administration | No tender procedure is required. | Not required | Own means | 275 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.5.4 | Office and Administration | No tender procedure is required. | Not required | Own means | 810 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.5.1 | Office and Administration | No tender procedure is required. | Not required | Own means | 112 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.5.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 459 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.5.4 | Office and Administration | No tender procedure is required. | Not required | Own means | 90 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.5.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 430 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.5.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 330 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.5.2 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 2000 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.5.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 480 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.5.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 220 |  |  |  |  | No milestones are to be achieved in the start-up period.
Note on E7: Georgios Charalampous: You will have to unite tenders of similar services/equipmnet to the minimum necessary regardless of the WPs or Actions that these may belong. Use the same nr (1,2,3) for the tenders you include in each line of the excel file if you plan to have them released under one procedure. The final number should be the number of the tenders you plan release in total.
Note on F7: Georgios Charalampous: Specify the type of the tender (open, restricted, direct, etc). The programme strongly advises the beneficiaries to use the maximum level of publicity. It is recommneded that for all the tenders of one budget line the type of the tender that coresponds to the total amount allocated to the budget line is followed.
Note on G7: Georgios Charalampous: The amount corresponding to the specific tender
Note on H7: Georgios Charalampous: The expected date of the tender release.
Note on I7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date tender closure
Note on J7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date of contract signature
Note on K7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): From the date of the tender launching until the contract signature
Note on L7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Explain the milestone to be achieved for this tender within the start-up period

## PB6
|  | Project Beneficiary 6 (PB6) | Regional Health Inspectorate |  | Project Start date: | 2017-11-01
|  | Beneficiary Country | Bulgaria |  | Project End date: | 2019-10-31
|  | Total Beneficiary budget in AF | 53378 |  | Project duration (months): | 23.9507
|  | Total Amount to be procured | 53378 |  | Start-up period end: | 2018-06-01
WP | Del. | Budget line | Brief description of the tender- Steps to be followed, etc | Tender Nr. | Type of tender | Amount of tender (€) | Estimated Date of launching (MM/YYYY) | Estimated Date of tender closure (MM/YYYY) | Estimated Date of Contract granting (MM/YYYY) | Estimated tender Procedure duration (months) | Milestone to be achieved within start-up period
WP3 | D3.6.1 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 25 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 2 | Collecting offers through public announcement | 6000 | 2018-07-01 | 2018-07-15 | 2018-07-25 | 1 | Contract for services signed
WP3 | D3.6.4 | External Expertise and Services |  | Tender 2 | Collecting offers through public announcement | 4000 | 2018-07-01 | 2018-07-15 | 2018-07-25 | 1 | Contract for services signed
WP4 | D4.6.1 | External Expertise and Services |  | Tender 2 | Collecting offers through public announcement | 2500 | 2018-07-01 | 2018-07-15 | 2018-07-25 | 1 | Contract for services signed
WP5 | D5.6.2 | External Expertise and Services |  | Tender 2 | Collecting offers through public announcement | 2500 | 2018-07-01 | 2018-07-15 | 2018-07-25 | 1 | Contract for services signed
WP6 | D6.6.3 | External Expertise and Services |  | Tender 2 | Collecting offers through public announcement | 3000 | 2018-07-01 | 2018-07-15 | 2018-07-25 | 1 | Contract for services signed
WP6 | D6.6.4 | External Expertise and Services |  | Tender 2 | Collecting offers through public announcement | 4000 | 2018-07-01 | 2018-07-15 | 2018-07-25 | 1 | Contract for services signed
WP4 | D4.6.2 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 3 | Direct contract | 3000 | 2018-09-01 | 2018-09-15 | 2018-09-20 | 1 | Contract for services signed
WP4 | D4.6.3 | External Expertise and Services |  | Tender 3 | Direct contract | 8000 | 2018-09-01 | 2018-09-15 | 2018-09-20 | 1 | Contract for services signed
WP6 | D6.6.4 | External Expertise and Services | A service contract for event organisation (catering, conference room, rent of equipment) will be contracted strictly following the Procurement Law. | Tender 1 | Direct contract | 260 | 2018-06-01 | 2018-06-15 | 2018-06-15 | 0,5 | Contract for services signed
WP1 | D1.6.4 | External Expertise and Services | A service contract for event organisation (catering, conference room, rent of equipment) will be contracted strictly following the Procurement Law. | Tender 1 | Direct contract | 160 | 2018-06-01 | 2018-06-15 | 2018-06-15 | 0,5 | Contract for services signed
WP2 | D2.6.4 | External Expertise and Services | No tender procedure is required. | Not required | Own means | 260 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.6.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 2250 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.6.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 1500 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.6.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 500 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.6.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 1500 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.6.1 | Staff Costs | No tender procedure is required. | Not required | Own means | 1500 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.6.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 3000 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.6.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 1430 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.6.1 | Staff Costs | No tender procedure is required. | Not required | Own means | 750 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.6.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 500 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.6.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 500 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.6.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 500 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.6.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 700 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.6.4 | Office and Administration | No tender procedure is required. | Not required | Own means | 175 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.6.1 | Office and Administration | No tender procedure is required. | Not required | Own means | 225 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.6.2 | Office and Administration | No tender procedure is required. | Not required | Own means | 1050 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.6.4 | Office and Administration | No tender procedure is required. | Not required | Own means | 214 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.6.1 | Office and Administration | No tender procedure is required. | Not required | Own means | 112 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.6.2 | Office and Administration | No tender procedure is required. | Not required | Own means | 112 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.6.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 105 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.6.2 | Office and Administration | No tender procedure is required. | Not required | Own means | 75 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.6.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 380 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.6.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 290 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.6.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 100 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.6.2 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 2000 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.6.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 140 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.6.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 70 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.6.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 20 |  |  |  |  | No milestones are to be achieved in the start-up period.
Note on E7: Georgios Charalampous: You will have to unite tenders of similar services/equipmnet to the minimum necessary regardless of the WPs or Actions that these may belong. Use the same nr (1,2,3) for the tenders you include in each line of the excel file if you plan to have them released under one procedure. The final number should be the number of the tenders you plan release in total.
Note on F7: Georgios Charalampous: Specify the type of the tender (open, restricted, direct, etc). The programme strongly advises the beneficiaries to use the maximum level of publicity. It is recommneded that for all the tenders of one budget line the type of the tender that coresponds to the total amount allocated to the budget line is followed.
Note on G7: Georgios Charalampous: The amount corresponding to the specific tender
Note on H7: Georgios Charalampous: The expected date of the tender release.
Note on I7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date tender closure
Note on J7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date of contract signature
Note on K7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): From the date of the tender launching until the contract signature
Note on L7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Explain the milestone to be achieved for this tender within the start-up period

## PB7
|  | Project Beneficiary 7 (PB7) | Association of Rhodope Municipalities |  | Project Start date: | 2017-11-01
|  | Beneficiary Country | Bulgaria |  | Project End date: | 2019-10-31
|  | Total Beneficiary budget in AF | 51282 |  | Project duration (months): | 23.9507
|  | Total Amount to be procured | 51282 |  | Start-up period end: | 2018-04-30
WP | Del. | Budget line | Brief description of the tender- Steps to be followed, etc | Tender Nr. | Type of tender | Amount of tender (€) | Estimated Date of launching (MM/YYYY) | Estimated Date of tender closure (MM/YYYY) | Estimated Date of Contract granting (MM/YYYY) | Estimated tender Procedure duration (months) | Milestone to be achieved within start-up period
WP2 | D2.7.3 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 1 | Direct | 9100 | 2018-07-15 | 2018-08-15 | 2018-09-15 | 2 | Completion of tender start of works
WP5 | D5.7.1 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 2 | Direct | 4500 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | No milestones are to be achieved in the start-up period.
WP5 | D5.7.3 | External Expertise and Services |  | Tender 2 | Direct | 6000 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | No milestones are to be achieved in the start-up period.
WP6 | D6.7.1 | External Expertise and Services |  | Tender 2 | Direct | 6000 | 2018-09-01 | 2018-09-30 | 2018-10-31 | 2 | No milestones are to be achieved in the start-up period.
WP6 | D6.7.4 | External Expertise and Services | No tender procedure is required. | Not required | Own means | 260 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.7.1 | Staff Costs | No tender procedure is required. | Not required | Own means | 3600 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.7.2 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Not required | Direct | 3250 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.7.2 | External Expertise and Services |  | Not required | Direct | 1000 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.7.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 1600 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.7.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 2000 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.7.5 | Staff Costs | No tender procedure is required. | Not required | Own means | 3600 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.7.1 | Staff Costs | No tender procedure is required. | Not required | Own means | 1800 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.7.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 900 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.7.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 2000 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.7.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 3200 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.7.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 790 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.7.5 | Office and Administration | No tender procedure is required. | Not required | Own means | 1132 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.7.1 | Office and Administration | No tender procedure is required. | Not required | Own means | 100 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.7.1 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 100 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.7.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 0 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.7.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 0 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.7.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 120 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.7.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 80 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP7 | D6.7.5 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 110 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP8 | D6.7.6 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 40 |  |  |  |  | No milestones are to be achieved in the start-up period.
Note on E7: Georgios Charalampous: You will have to unite tenders of similar services/equipmnet to the minimum necessary regardless of the WPs or Actions that these may belong. Use the same nr (1,2,3) for the tenders you include in each line of the excel file if you plan to have them released under one procedure. The final number should be the number of the tenders you plan release in total.
Note on F7: Georgios Charalampous: Specify the type of the tender (open, restricted, direct, etc). The programme strongly advises the beneficiaries to use the maximum level of publicity. It is recommneded that for all the tenders of one budget line the type of the tender that coresponds to the total amount allocated to the budget line is followed.
Note on G7: Georgios Charalampous: The amount corresponding to the specific tender
Note on H7: Georgios Charalampous: The expected date of the tender release.
Note on I7: Estimated date tender closure
Note on J7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date of contract signature
Note on K7: From the date of the tender launching until the contract signature
Note on L7: Explain the milestone to be achieved for this tender within the start-up period

## PB8
|  | Project Beneficiary 8 (PB8) | Municipality of Krumovgrad |  | Project Start date: | 2017-11-01
|  | Beneficiary Country | Bulgaria |  | Project End date: | 2019-10-31
|  | Total Beneficiary budget in AF | 226623 |  | Project duration (months): | 23.9507
|  | Total Amount to be procured | 226623 |  | Start-up period end: | 2018-04-30
WP | Del. | Budget line | Brief description of the tender- Steps to be followed, etc | Tender Nr. | Type of tender | Amount of tender (€) | Estimated Date of launching (MM/YYYY) | Estimated Date of tender closure (MM/YYYY) | Estimated Date of Contract granting (MM/YYYY) | Estimated tender Procedure duration (months) | Milestone to be achieved within start-up period
WP1 | D1.8.1 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 1 | direct assignment | 5000
WP1 | D1.8.5 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 2 | direct assignment | 5000 | 2018-04-01 | 2018-04-30 | 2018-05-25 | 1.5 | Contracted; Date: 25.05.2018
WP2 | D2.8.5 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 3 | collecting bids with an announcement | 560 | 2018-05-01 | 2018-06-01 | 2018-06-28 | 2 | Signing a contract in June
WP2 | D2.8.5 | External Expertise and Services |  | Tender 3 | collecting bids with an announcement | 500 | 2018-05-01 | 2018-06-01 | 2018-06-28 | 2 | Signing a contract in June
WP4 | D4.8.5 | External Expertise and Services |  | Tender 3 | collecting bids with an announcement | 610 | 2018-05-01 | 2018-06-01 | 2018-06-28 | 2 | Signing a contract in June
WP4 | D4.8.5 | External Expertise and Services |  | Tender 3 | collecting bids with an announcement | 300 | 2018-05-01 | 2018-06-01 | 2018-06-28 | 2 | Signing a contract in June
WP5 | D5.8.3 | External Expertise and Services |  | Tender 3 | collecting bids with an announcement | 560 | 2018-05-01 | 2018-06-01 | 2018-06-28 | 2 | Signing a contract in June
WP5 | D5.8.3 | External Expertise and Services |  | Tender 3 | collecting bids with an announcement | 1000 | 2018-05-01 | 2018-06-01 | 2018-06-28 | 2 | Signing a contract in June
WP1 | D1.8.4 | External Expertise and Services |  | Tender 3 | collecting bids with an announcement | 160 | 2018-05-01 | 2018-06-01 | 2018-06-28 | 2 | Signing a contract in June
WP3 | D3.8.3 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 25 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 4 | public competition | 20000 | 2018-06-01 | 2018-09-15 | 2018-10-01 | 4 | Completion of tender and start of works
WP5 | D5.8.4 | External Expertise and Services |  | Tender 4 | public competition | 30000 | 2018-06-01 | 2018-09-15 | 2018-10-01 | 4 | Completion of tender
WP4 | D4.8.4 | Infrastructure and Works | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 25 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 5 | public competition | 69856 | 2017-12-20 | 2018-04-03 | 2018-05-08 | 4.5 | Contracted; Date: 08.05.2018
WP4 | D4.8.3 | Equipment | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 6 | direct assignment | 2000 | 2018-03-01 | 2018-04-15 | 2018-05-31 | 3 | Signing a contract in June
WP4 | D4.8.4 | Equipment |  | Tender 6 | direct assignment | 3350 | 2018-03-01 | 2018-04-15 | 2018-05-31 | 3 | Signing a contract in June
WP4 | D4.8.4 | Equipment | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 25 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 7 | public competition | 46016 | 2018-05-01 | 2018-09-01 | 2018-09-15 | 4.5 | Completion of tender
WP4 | D4.8.2 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 8 | direct assignment | 2500 | 2018-05-15 | 2018-06-15 | 2018-06-30 | 1.5 | Launch of Tender
WP4 | D4.8.4 | Equipment | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 9 | collecting bids with an announcement | 2847 | 2018-02-05 | 2018-04-02 | 2018-04-20 | 2.5 | Contracted Date: 20.04.2018
WP4 | D4.8.4 | Equipment | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 9 | collecting bids with an announcement | 20431 | 2018-02-05 | 2018-04-02 | 2018-04-20 | 2.5 | Contracted Date: 20.04.2018
WP6 | D6.8.3 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 10 | direct assignment | 3000 | 2019-06-01 | 2019-06-30 | 2019-07-15 | 1.5 | No milestones are to be achieved in the start-up period
WP1 | D1.8.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 380 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.8.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 290 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.8.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 100 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.8.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 340 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.8.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 110 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.8.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 40 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.8.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 3096 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.8.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 750 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.8.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 600 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.8.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 720 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.8.5 | Staff Costs | No tender procedure is required. | Not required | Own means | 960 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.8.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 300 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.8.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 858 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.8.5 | Staff Costs | No tender procedure is required. | Not required | Own means | 750 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.8.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 1020 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.8.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 300 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.8.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 300 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.8.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 500 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.8.2 | Office and Administration | No tender procedure is required. | Not required | Own means | 458 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.8.4 | Office and Administration | No tender procedure is required. | Not required | Own means | 108 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.8.5 | Office and Administration | No tender procedure is required. | Not required | Own means | 128 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.8.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 128 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.8.2 | Office and Administration | No tender procedure is required. | Not required | Own means | 128 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.8.5 | Office and Administration | No tender procedure is required. | Not required | Own means | 107 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.8.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 153 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.8.4 | Office and Administration | No tender procedure is required. | Not required | Own means | 153 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.8.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 81 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.8.4 | Office and Administration | No tender procedure is required. | Not required | Own means | 75 |  |  |  |  | No milestones are to be achieved in the start-up period.
Note on E7: Georgios Charalampous: You will have to unite tenders of similar services/equipmnet to the minimum necessary regardless of the WPs or Actions that these may belong. Use the same nr (1,2,3) for the tenders you include in each line of the excel file if you plan to have them released under one procedure. The final number should be the number of the tenders you plan release in total.
Note on F7: Georgios Charalampous: Specify the type of the tender (open, restricted, direct, etc). The programme strongly advises the beneficiaries to use the maximum level of publicity. It is recommneded that for all the tenders of one budget line the type of the tender that coresponds to the total amount allocated to the budget line is followed.
Note on G7: Georgios Charalampous: The amount corresponding to the specific tender
Note on H7: Georgios Charalampous: The expected date of the tender release.
Note on I7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date tender closure
Note on J7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date of contract signature
Note on K7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): From the date of the tender launching until the contract signature
Note on L7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Explain the milestone to be achieved for this tender within the start-up period

## PB9
|  | Project Beneficiary 9 (PB9) | Municipality of Momchilgrad |  | Project Start date: | 2017-11-01
|  | Beneficiary Country | Bulgaria |  | Project End date: | 2019-10-31
|  | Total Beneficiary budget in AF | 223495 |  | Project duration (months): | 23.9507
|  | Total Amount to be procured | 223495 |  | Start-up period end: | 2018-04-30
WP | Del. | Budget line | Brief description of the tender- Steps to be followed, etc | Tender Nr. | Type of tender | Amount of tender (€) | Estimated Date of launching (MM/YYYY) | Estimated Date of tender closure (MM/YYYY) | Estimated Date of Contract granting (MM/YYYY) | Estimated tender Procedure duration (months) | Milestone to be achieved within start-up period
WP1 | D1.9.1 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 1 | Direct agreement under Art. 20, Para. 4, item 3 of the Public Procurement Act | 5000
WP1 | D1.9.4 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 2 | Direct agreement under Art. 20, Para. 4, item 3 of the Public Procurement Act | 160 | 2018-09-15 | 2018-10-15 | 2018-10-31 | 1.5 | Completion of tender
WP2 | D2.9.5 | External Expertise and Services |  | Tender 2 | Direct agreement under Art. 20, Para. 4, item 3 of the Public Procurement Act | 560 | 2018-09-15 | 2018-10-15 | 2018-10-31 | 1.5 | Completion of tender
WP2 | D2.9.5 | External Expertise and Services |  | Tender 2 | Direct agreement under Art. 20, Para. 4, item 3 of the Public Procurement Act | 500 | 2018-09-15 | 2018-10-15 | 2018-10-31 | 1.5 | Completion of tender
WP4 | D4.9.5 | External Expertise and Services |  | Tender 2 | Direct agreement under Art. 20, Para. 4, item 3 of the Public Procurement Act | 610 | 2018-09-15 | 2018-10-15 | 2018-10-31 | 1.5 | Completion of tender
WP4 | D4.9.5 | External Expertise and Services |  | Tender 2 | Direct agreement under Art. 20, Para. 4, item 3 of the Public Procurement Act | 300 | 2018-09-15 | 2018-10-15 | 2018-10-31 | 1.5 | Completion of tender
WP5 | D5.9.3 | External Expertise and Services |  | Tender 2 | Direct agreement under Art. 20, Para. 4, item 3 of the Public Procurement Act | 560 | 2018-09-15 | 2018-10-15 | 2018-10-31 | 1.5 | Completion of tender
WP5 | D5.9.3 | External Expertise and Services |  | Tender 2 | Direct agreement under Art. 20, Para. 4, item 3 of the Public Procurement Act | 1500 | 2018-09-15 | 2018-10-15 | 2018-10-31 | 1.5 | Completion of tender
WP3 | D3.9.3 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 25 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 3 | Public competition under Art. 20, Para. 2, p. 2 of the Public Procurement Act | 20000 | 2018-09-15 | 2018-11-15 | 2018-12-15 | 4 | Completion of tender and start of works
WP5 | D5.9.4 | External Expertise and Services |  | Tender 3 | Public competition under Art. 20, Para. 2, p. 2 of the Public Procurement Act | 30000 | 2018-09-15 | 2018-11-15 | 2018-12-15 | 4 | Completion of tender
WP4 | D4.9.4 | Equipment | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 25 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 4 | Public competition under Art. 20, Para. 2, p. 2 of the Public Procurement Act | 82752.59 | 2018-07-01 | 2018-09-30 | 2018-10-15 | 4 | Completion of tender and start of works
WP4 | D4.9.4 | Infrastructure and Works | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 25 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 5 | Public competition under Art. 20, Para. 2, p. 1 of the Public Procurement Act | 59747.41 | 2018-02-07 | 2018-03-08 | 2018-04-24 | 4 | Completion of tender and start of works
WP4 | D4.9.3 | Equipment | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 6 | Direct agreement under Art. 20, Para. 4, item 3 of the Public Procurement Act | 2000 | 2018-09-15 | 2018-10-15 | 2018-10-31 | 1.5 | Completion of tender
WP6 | D6.9.3 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 7 | Direct agreement under Art. 20, Para. 4, item 3 of the Public Procurement Act | 3000 | 2019-02-15 | 2019-03-15 | 2019-03-31 | 1.5 | Completion of tender
WP4 | D4.9.2 | External Expertise and Services | 1. Preparation of tender documents 2. Approval Decision on launching the Call and on approving the tender documents 3. Publication of the tender – the deadline for the submission of offers is estimated approximately to 5 days 4. Evaluation of offers - Approval of results 5. Signing Contract | Tender 8 | Direct agreement under Art. 20, Para. 4, item 3 of the Public Procurement Act | 2500 | 2019-04-15 | 2019-05-15 | 2019-05-31 | 1.5 | Launch of Tender
WP1 | D1.9.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 3096 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.9.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 2580 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.9.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 600 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.9.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 720 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.9.5 | Staff Costs | No tender procedure is required. | Not required | Own means | 960 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.9.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 300 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.9.2 | Staff Costs | No tender procedure is required. | Not required | Own means | 858 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.9.5 | Staff Costs | No tender procedure is required. | Not required | Own means | 750 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.9.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 1020 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.9.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 300 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.9.3 | Staff Costs | No tender procedure is required. | Not required | Own means | 300 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.9.4 | Staff Costs | No tender procedure is required. | Not required | Own means | 500 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.9.4 | Office and Administration | No tender procedure is required. | Not required | Own means | 108 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP2 | D2.9.5 | Office and Administration | No tender procedure is required. | Not required | Own means | 128 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP3 | D3.9.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 128 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.9.2 | Office and Administration | No tender procedure is required. | Not required | Own means | 128 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP4 | D4.9.5 | Office and Administration | No tender procedure is required. | Not required | Own means | 107 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.9.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 153 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP5 | D5.9.4 | Office and Administration | No tender procedure is required. | Not required | Own means | 153 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.9.3 | Office and Administration | No tender procedure is required. | Not required | Own means | 81 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.9.4 | Office and Administration | No tender procedure is required. | Not required | Own means | 75 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.9.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 380 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.9.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 290 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP1 | D1.9.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 100 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.9.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 340 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.9.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 110 |  |  |  |  | No milestones are to be achieved in the start-up period.
WP6 | D6.9.4 | Travel and Accommodation | No tender procedure is required. | Not required | Own means | 40 |  |  |  |  | No milestones are to be achieved in the start-up period.
Note on E7: Georgios Charalampous: You will have to unite tenders of similar services/equipmnet to the minimum necessary regardless of the WPs or Actions that these may belong. Use the same nr (1,2,3) for the tenders you include in each line of the excel file if you plan to have them released under one procedure. The final number should be the number of the tenders you plan release in total.
Note on F7: Georgios Charalampous: Specify the type of the tender (open, restricted, direct, etc). The programme strongly advises the beneficiaries to use the maximum level of publicity. It is recommneded that for all the tenders of one budget line the type of the tender that coresponds to the total amount allocated to the budget line is followed.
Note on G7: Georgios Charalampous: The amount corresponding to the specific tender
Note on H7: Georgios Charalampous: The expected date of the tender release.
Note on I7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date tender closure
Note on J7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date of contract signature
Note on K7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): From the date of the tender launching until the contract signature
Note on L7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Explain the milestone to be achieved for this tender within the start-up period

## PB10
|  | Project Beneficiary 10 (PB10) | 0 |  | Project Start date: | 2017-11-01
|  | Beneficiary Country | 0 |  | Project End date: | 2019-10-31
|  | Total Beneficiary budget in AF | 0 |  | Project duration (months): | 23.9507
|  | Total Amount to be procured | 0 |  | Start-up period end: | 2018-04-30
WP | Del. | Budget line | Brief description of the tender- Steps to be followed, etc | Tender Nr. | Type of tender | Amount of tender (€) | Estimated Date of launching (MM/YYYY) | Estimated Date of tender closure (MM/YYYY) | Estimated Date of Contract granting (MM/YYYY) | Estimated tender Procedure duration (months) | Milestone to be achieved within start-up period
Note on E7: Georgios Charalampous: You will have to unite tenders of similar services/equipmnet to the minimum necessary regardless of the WPs or Actions that these may belong. Use the same nr (1,2,3) for the tenders you include in each line of the excel file if you plan to have them released under one procedure. The final number should be the number of the tenders you plan release in total.
Note on F7: Georgios Charalampous: Specify the type of the tender (open, restricted, direct, etc). The programme strongly advises the beneficiaries to use the maximum level of publicity. It is recommneded that for all the tenders of one budget line the type of the tender that coresponds to the total amount allocated to the budget line is followed.
Note on G7: Georgios Charalampous: The amount corresponding to the specific tender
Note on H7: Georgios Charalampous: The expected date of the tender release.
Note on I7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date tender closure
Note on J7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Estimated date of contract signature
Note on K7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): From the date of the tender launching until the contract signature
Note on L7: ΧΑΡΑΛΑΜΠΟΥΣ ΓΙΩΡΓΟΣ (CHARALAMPOUS GIORGOS): Explain the milestone to be achieved for this tender within the start-up period

## VF (hidden)
Not required
Priority Axis |  |  |  | Greece |  | Staff Costs |  |  |  | Tender 1
1. A Competitive and Innovative Cross-Border Area | Pr.Axis1 |  |  | Bulgaria |  | Office and Administration |  |  |  | Tender 2
2. A Sustainable and Climate adaptable Cross-Border area | Pr.Axis2 |  |  |  |  | Travel and Accommodation |  |  |  | Tender 3
3. A Better interconnected Cross-Border Area | Pr.Axis3 |  |  |  |  | External Expertise and Services |  |  |  | Tender 4
4. A Socially Inclusive Cross-Border Area | Pr.Axis4 |  |  |  |  | Equipment |  |  |  | Tender 5
5. Technical Assistance | Pr.Axis5 |  |  |  |  | Infrastructure and Works |  |  |  | Tender 6
Tender 7
Tender 8
3. A Better interconnected Cross-Border Area | Pr.Axis3 | [8 empty] | Tender 9
Tender 10
2. A Sustainable and Climate adaptable Cross-Border area | Pr.Axis2 |  |  | ` | [5 empty] | Tender 11
4. A Socially Inclusive Cross-Border Area | Pr.Axis4 | [8 empty] | Tender 12
Tender 13
Tender 14
Tender 15
Investment Priority
(3a) | Promoting entrepreneurship, in particular by facilitating the economic exploitation of new ideas and fostering the creation of new firms, including through business incubators
(3d) | Supporting the capacity of SMEs to grow in regional, national and international markets, and to engage in innovation processes
(5b) | Promoting investment to address specific risks, ensuring disaster resilience and developing disaster management systems
(6c) | Conserving, protecting, promoting and developing natural and cultural heritage
(6d) | Protecting and restoring biodiversity, soil protection and restoration and promoting ecosystem services including NATURA 2000 and green infrastructures
(6f) | Promoting innovative technologies to improve environmental protection and resource efficiency in the waste sector, water sector, soil protection or to reduce air pollution.
(7d) | Enhancing regional mobility by connecting secondary and tertiary nodes to TEN-T infrastructure, including multimodal nodes.
(9a) | Investing in health and social infrastructure which contribute to national, regional and local development, reducing inequalities in terms of health status, promoting social inclusion through improved access to social, cultural and recreational services and the transition from institutional to community-based services.
(9c) | Providing support for social enterprises
(10.) | Technical Assistance
P1WP1 | P1WP2 | P1WP3 | P1WP4 | P1WP5 | P1WP6 |  | P6WP1 | P6WP2 | P6WP3 | P6WP4 | P6WP5 | P6WP6
D1.1.1 | D2.1.1 | D3.1.1 | D4.1.1 | D5.1.1 | D6.1.1 |  | D1.6.1 | D2.6.1 | D3.6.1 | D4.6.1 | D5.6.1 | D6.6.1
D1.1.2 | D2.1.2 | D3.1.2 | D4.1.2 | D5.1.2 | D6.1.2 |  | D1.6.2 | D2.6.2 | D3.6.2 | D4.6.2 | D5.6.2 | D6.6.2
D1.1.3 | D2.1.3 | D3.1.3 | D4.1.3 | D5.1.3 | D6.1.3 |  | D1.6.3 | D2.6.3 | D3.6.3 | D4.6.3 | D5.6.3 | D6.6.3
D1.1.4 | D2.1.4 | D3.1.4 | D4.1.4 | D5.1.4 | D6.1.4 |  | D1.6.4 | D2.6.4 | D3.6.4 | D4.6.4 | D5.6.4 | D6.6.4
D1.1.5 | D2.1.5 | D3.1.5 | D4.1.5 | D5.1.5 | D6.1.5 |  | D1.6.5 | D2.6.5 | D3.6.5 | D4.6.5 | D5.6.5 | D6.6.5
P2WP1 | P2WP2 | P2WP3 | P2WP4 | P2WP5 | P2WP6 |  | P7WP1 | P7WP2 | P7WP3 | P7WP4 | P7WP5 | P7WP6
D1.2.1 | D2.2.1 | D3.2.1 | D4.2.1 | D5.2.1 | D6.2.1 |  | D1.7.1 | D2.7.1 | D3.7.1 | D4.7.1 | D5.7.1 | D6.7.1
D1.2.2 | D2.2.2 | D3.2.2 | D4.2.2 | D5.2.2 | D6.2.2 |  | D1.7.2 | D2.7.2 | D3.7.2 | D4.7.2 | D5.7.2 | D6.7.2
D1.2.3 | D2.2.3 | D3.2.3 | D4.2.3 | D5.2.3 | D6.2.3 |  | D1.7.3 | D2.7.3 | D3.7.3 | D4.7.3 | D5.7.3 | D6.7.3
D1.2.4 | D2.2.4 | D3.2.4 | D4.2.4 | D5.2.4 | D6.2.4 |  | D1.7.4 | D2.7.4 | D3.7.4 | D4.7.4 | D5.7.4 | D6.7.4
D1.2.5 | D2.2.5 | D3.2.5 | D4.2.5 | D5.2.5 | D6.2.5 |  | D1.7.5 | D2.7.5 | D3.7.5 | D4.7.5 | D5.7.5 | D6.7.5
P3WP1 | P3WP2 | P3WP3 | P3WP4 | P3WP5 | P3WP6 |  | P8WP1 | P8WP2 | P8WP3 | P8WP4 | P8WP5 | P8WP6
D1.3.1 | D2.3.1 | D3.3.1 | D4.3.1 | D5.3.1 | D6.3.1 |  | D1.8.1 | D2.8.1 | D3.8.1 | D4.8.1 | D5.8.1 | D6.8.1
D1.3.2 | D2.3.2 | D3.3.2 | D4.3.2 | D5.3.2 | D6.3.2 |  | D1.8.2 | D2.8.2 | D3.8.2 | D4.8.2 | D5.8.2 | D6.8.2
D1.3.3 | D2.3.3 | D3.3.3 | D4.3.3 | D5.3.3 | D6.3.3 |  | D1.8.3 | D2.8.3 | D3.8.3 | D4.8.3 | D5.8.3 | D6.8.3
D1.3.4 | D2.3.4 | D3.3.4 | D4.3.4 | D5.3.4 | D6.3.4 |  | D1.8.4 | D2.8.4 | D3.8.4 | D4.8.4 | D5.8.4 | D6.8.4
D1.3.5 | D2.3.5 | D3.3.5 | D4.3.5 | D5.3.5 | D6.3.5 |  | D1.8.5 | D2.8.5 | D3.8.5 | D4.8.5 | D5.8.5 | D6.8.5
P4WP1 | P4WP2 | P4WP3 | P4WP4 | P4WP5 | P4WP6 |  | P9WP1 | P9WP2 | P9WP3 | P9WP4 | P9WP5 | P9WP6
D1.4.1 | D2.4.1 | D3.4.1 | D4.4.1 | D5.4.1 | D6.4.1 |  | D1.9.1 | D2.9.1 | D3.9.1 | D4.9.1 | D5.9.1 | D6.9.1
D1.4.2 | D2.4.2 | D3.4.2 | D4.4.2 | D5.4.2 | D6.4.2 |  | D1.9.2 | D2.9.2 | D3.9.2 | D4.9.2 | D5.9.2 | D6.9.2
D1.4.3 | D2.4.3 | D3.4.3 | D4.4.3 | D5.4.3 | D6.4.3 |  | D1.9.3 | D2.9.3 | D3.9.3 | D4.9.3 | D5.9.3 | D6.9.3
D1.4.4 | D2.4.4 | D3.4.4 | D4.4.4 | D5.4.4 | D6.4.4 |  | D1.9.4 | D2.9.4 | D3.9.4 | D4.9.4 | D5.9.4 | D6.9.4
D1.4.5 | D2.4.5 | D3.4.5 | D4.4.5 | D5.4.5 | D6.4.5 |  | D1.9.5 | D2.9.5 | D3.9.5 | D4.9.5 | D5.9.5 | D6.9.5
P5WP1 | P5WP2 | P5WP3 | P5WP4 | P5WP5 | P5WP6 |  | P10WP1 | P10WP2 | P10WP3 | P10WP4 | P10WP5 | P10WP6
D1.5.1 | D2.5.1 | D3.5.1 | D4.5.1 | D5.5.1 | D6.5.1 |  | D1.10.1 | D2.10.1 | D3.10.1 | D4.10.1 | D5.10.1 | D6.10.1
D1.5.2 | D2.5.2 | D3.5.2 | D4.5.2 | D5.5.2 | D6.5.2 |  | D1.10.2 | D2.10.2 | D3.10.2 | D4.10.2 | D5.10.2 | D6.10.2
D1.5.3 | D2.5.3 | D3.5.3 | D4.5.3 | D5.5.3 | D6.5.3 |  | D1.10.3 | D2.10.3 | D3.10.3 | D4.10.3 | D5.10.3 | D6.10.3
D1.5.4 | D2.5.4 | D3.5.4 | D4.5.4 | D5.5.4 | D6.5.4 |  | D1.10.4 | D2.10.4 | D3.10.4 | D4.10.4 | D5.10.4 | D6.10.4
D1.5.5 | D2.5.5 | D3.5.5 | D4.5.5 | D5.5.5 | D6.5.5 |  | D1.10.5 | D2.10.5 | D3.10.5 | D4.10.5 | D5.10.5 | D6.10.5